## Team plan and work distribution
Parallel Programming - 22KHMT
Plan and work distribution
Group: 06
· 22127008 - Đặng Châu Anh
· 22127170 - Trần Dịu Huyền
· 22127359 - Chu Thúy Quỳnh
Plan and work distribution
Start | End | Task | Owner
24/11/2025 | 30/11/2025 | - Problem Statement, CIFAR-10 overview, Autoencoder architecture. | Chu Thúy Quỳnh
|  | - Implement Conv2D, ReLU, MaxPool, Upsample, MSE Loss. - Weight initialization, forward pass, backward pass, save/load weights | Trần Dịu Huyền
|  | - Implement CIFAR-10 Dataset class, binary parsing, normalization, batching, shuffling. - Train CPU baseline for 20 epochs, record time & loss. | Đặng Châu Anh
01/12/2025 | 7/12/2025 | - GPU Memory Management. - Implement: Convolution, ReLU, MaxPooling, Upsampling, MSE Loss. | Chu Thúy Quỳnh
|  | - Complete full forward pass on GPU. - Implement gradient kernels + SGD weight update. | Đặng Châu Anh
|  | - Set up loss/time logging for GPU training. - Write report phase 1. | Trần Dịu Huyền
8/12/2025 | 14/12/2025 | - Try to apply 2–3 optimizations and and choose the most effective method. | Đặng Châu Anh Trần Dịu Huyền
|  | - Extract latent vectors, train SVM, compute accuracy. - Write report phase 2. | Chu Thúy Quỳnh
15/12/2025 | 17/12/2025 | - Comprehensive Performance Analysis. - Write report phase 3. | Đặng Châu Anh
|  | - Lessons Learned and Challenges Overcome. - Write report phase 4. | Chu Thúy Quỳnh
|  | - Conclusion and Future Work. - Write README.md | Trần Dịu Huyền
18/12/2025 | 20/12/2025 | - Combine all modules, format file. - Video. - Slide. | All members